## Training Details
Android Training:Main Training Details
Last Updated: 2014/1/6 | [5 empty] | Total Hours | Total Days | Duration |  | Actual Hours |  |  | ● | Start (spanning multiple days)
[5 empty] | iBJ (Basic Android Study and Exercises) [excluding optional] | 111.5 | 27.875 | 1/6～1/18 |  | 0 |  |  | ★ | End (spanning just one day, or end of multiple days)
[5 empty] | Estimated Hours for Optional Topics | 86
|  | ◆Indispensable(Very Essential) Exercises | [7 empty] | Items to Fill Up
|  | Optional Topics (May be done only if actual has been faster than planned) |  |  | Planned |  |  |  | Actual |  |  |  | 1月
| TOPIC |  |  |  | Estimated Hours |  | Planned Start | Planned End | Actual Hours | Actual Start | Actual End | Status | 2014-01-06 | 2014-01-07 | 2014-01-08 | 2014-01-09 | 2014-01-10 | 2014-01-11 | 2014-01-12 | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-16 | 2014-01-17 | 2014-01-18 | 2014-01-19 | 2014-01-20 | 2014-01-21 | 2014-01-22 | 2014-01-23 | 2014-01-24 | 2014-01-25 | 2014-01-26
[13 empty] | 2014-01-06 | 2014-01-07 | 2014-01-08 | 2014-01-09 | 2014-01-10 | 2014-01-11 | 2014-01-12 | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-16 | 2014-01-17 | 2014-01-18 | 2014-01-19 | 2014-01-20 | 2014-01-21 | 2014-01-22 | 2014-01-23 | 2014-01-24 | 2014-01-25 | 2014-01-26
iBJ | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
iBP | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
| Trainee: Cess | [11 empty] | 2014-01-06: D1; 2014-01-07: D2; 2014-01-08: D3; 2014-01-09: D4; 2014-01-10: D5; 2014-01-14: D6; 2014-01-15: D7; 2014-01-16: D8; 2014-01-17: D9; 2014-01-18: D10
[13 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
| 1) | DEV Environment Setup/Preparation |  |  | 2 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  |  | ⇒ JDK (v7u7) ⇒ Eclipse (4.2.1) ⇒ Android SDK (http://developer.android.com/sdk/index.html) - SDK Platforms - Install from Gingerbread(2.3.3) to Latest(4.4) [API 10-19] ⇒ Install Eclipse ADT Plugin |  |  | 2 | [5 empty] | Not started
| 2) | Updated Training Based on Coursera: https://www.coursera.org/course/android |  |  | 31 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 2.1) | The Android Platform |  |  | 1 | [5 empty] | Finished
|  | 2.2) | The Android Development Environment |  |  | 1 | [5 empty] | Finished
|  | 2.3) | Application Fundamentals |  |  | 1 | [5 empty] | Finished
|  | 2.4) | The Activity Class |  |  | 2 | [5 empty] | Finished
|  | 2.5) | The Intent Class |  |  | 2 | [5 empty] | Finished
|  | 2.6) | Permissions | 1206-added |  | 1 | [5 empty] | Finished
|  | 2.9) | User Interface Classes - Part I |  |  | 4 | [5 empty] | Finished
|  | 2.7) | The Fragment Class | 1206-added |  | 2 | [5 empty] | Ongoing
|  | 2.8) | Bitmaps | 1206-added |  | 2 | [5 empty] | Not started
|  | 2.10) | User Interface Classes - Part II |  |  | 4 | [5 empty] | Not started
|  | 2.11) | Data Storage, File System and Preferences | 1206-added |  | 2 | [5 empty] | Not started
|  | 2.12) | Threads, Messages & Thread Pools | 1206-added |  | 2 | [5 empty] | Not started
|  | 2.13) | Networking |  |  | 3 | [5 empty] | Not started
|  | 2.14) | The ContentProvider Class |  |  | 2 | [5 empty] | Not started
|  | 2.17) | Build and Deployment | 1206-added |  | 2 | [5 empty] | Not started
| 3) | Clicker Specific Training Topics |  |  | 12 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 3.1) | Location & Maps (using Google Play services) |  | optional | 2 | [5 empty] | Not started
|  | 3.2) | Camera | 1206-added | optional | 4 | [5 empty] | Not started
|  | 3.3) | Playing Media |  | optional | 4 | [5 empty] | Not started
|  | 3.4) | WebView | 1206-added | optional | 2 | [5 empty] | Not started
| 4) | Optional Training Topics |  |  | 28 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 4.1) | The BroadcastReceiver Class |  | optional | 2 | [5 empty] | Not started
|  | 4.2) | Notifications & Alarms |  | optional | 2 | [5 empty] | Not started
|  | 4.3) | Multi-touch & Gestures+ |  | optional | 2 | [5 empty] | Not started
|  | 4.4) | Graphics & Animation |  | optional | 4 | [5 empty] | Not started
|  | 4.5) | MultiMedia |  | optional | 2 | [5 empty] | Not started
|  | 4.6) | Sensors |  | optional | 2 | [5 empty] | Not started
|  | 4.7) | The Service Class |  | optional | 2 | [5 empty] | Not started
|  | 4.8) | Telephony |  | optional | 2 | [5 empty] | Not started
|  | 4.9) | Record and Play Audio |  | optional | 2 | [5 empty] | Not started
|  | 4.10) | Localization | 1206-added | optional | 2 | [5 empty] | Not started
|  | 4.11) | URL Scheme handling | 1206-added | optional | 2 | [5 empty] | Not started
|  | 4.12) | Testing | 1206-added | optional | 4 | [5 empty] | Not started
| 5) | Situational Training Topics |  |  | 40 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 5.1) | OpenGL |  | optional | 8 | [5 empty] | Not started
|  | 5.2) | Live Folders |  | optional | 2 | [5 empty] | Not started
|  | 5.3) | Local Search |  | optional | 2 | [5 empty] | Not started
|  | 5.4) | Global Search |  | optional | 2 | [5 empty] | Not started
|  | 5.5) | Speech to Text |  | optional | 4 | [5 empty] | Not started
|  | 5.6) | Canvas |  | optional | 4 | [5 empty] | Not started
|  | 5.7) | Custom Permissions |  | optional | 4 | [5 empty] | Not started
|  | 5.8) | Homescreen Widgets |  | optional | 6
|  | 5.9) | MediaStore |  | optional | 4
|  | 5.10) | Adapters |  | optional | 4 | [5 empty] | Not started
| 6) | Updated Exercises |  |  | 54 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 6.1) | ◆The Activity Class |  |  | 1 | [5 empty] | Not started
|  | 6.2) | ◆Permissions |  |  | 1 | [5 empty] | Not started
|  | 6.3) | ◆User Interface Classes - Part I |  |  | 4 | [5 empty] | Not started
|  | 6.4) | ◆The Fragment Class |  |  | 4 | [5 empty] | Not started
|  | 6.5) | ◆Bitmaps |  |  | 4 | [5 empty] | Not started
|  | 6.6) | ◆User Interface Classes - Part II |  |  | 6 | [5 empty] | Not started
|  | 6.7) | ◆Data Storage, File System and Preferences |  |  | 4 | [5 empty] | Not started
|  | 6.8) | Threads, Messages & Thread Pools |  |  | 4 | [5 empty] | Not started
|  | 6.9) | Networking |  |  | 4 | [5 empty] | Not started
|  | 6.10) | The ContentProvider Class |  |  | 6 | [5 empty] | Not started
|  | 6.11) | Location and Maps |  |  | 4 | [5 empty] | Not started
|  | 6.12) | Camera |  |  | 4 | [5 empty] | Not started
|  | 6.13) | Playing Media |  |  | 2 | [5 empty] | Not started
|  | 6.14) | Webview |  |  | 6 | [5 empty] | Not started
| 7) | Optional Additional Exercises (from Previous) |  |  | 30.5 | [6 empty] | Not started | bar: 2014-01-06 to 2014-01-10; 2014-01-14 to 2014-01-18; 2014-01-20 to 2014-01-24
|  | 7.1) | ◆Application Lifecycles |  |  | 1 | [5 empty] | Not started
|  | 7.2) | ◆UI Mosaic |  |  | 1 | [5 empty] | Not started
|  | 7.3) | ◆Layout Mosaic |  |  | 1 | [5 empty] | Not started
|  | 7.4) | ◆Resources |  |  | 1 | [5 empty] | Not started
|  | 7.5) | ◆Intents |  |  | 1.5 | [5 empty] | Not started
|  | 7.6) | ◆Menu Mosaic |  |  | 2 | [5 empty] | Not started
|  | 7.7) | ◆Dialogs |  |  | 2 | [5 empty] | Not started
|  | 7.8) | ◆Preferences Mosaic |  |  | 2 | [5 empty] | Not started
|  | 7.9) | ◆Animation - layout |  |  | 2 | [5 empty] | Not started
|  | 7.10) | ◆Animation - view |  |  | 2 | [5 empty] | Not started
|  | 7.11) | ◆AsyncTask |  |  | 2 | [5 empty] | Not started
|  | 7.12) | ◆Adapters |  |  | 1 | [5 empty] | Not started
|  | 7.13) | ◆Content Providers |  |  | 2 | [5 empty] | Not started
|  | 7.14) | ◆HTTP (Get) |  |  | 1 | [5 empty] | Not started
|  | 7.15) | Service (AIDL) |  | optional | 1.5 | [5 empty] | Not started
|  | 7.16) | Play Video |  |  | 1 | [5 empty] | Not started
|  | 7.17) | Record and Play audio |  | optional | 1.5 | [5 empty] | Not started
|  | 7.18) | MediaStore |  |  | 1 | [5 empty] | Not started
|  | 7.19) | Custom Permissions |  | optional | 0.5 | [5 empty] | Not started
|  | 7.20) | Maps & Locations |  |  | 1 | [5 empty] | Not started
|  | 7.21) | Telephony - SMS |  | optional | 0.5 | [5 empty] | Not started
|  | 7.22) | Telephony - Call |  | optional | 0.5 | [5 empty] | Not started
|  | 7.23) | Homescreen Widget |  | optional | 1.5 | [5 empty] | Not started
[13 empty] | 2014-01-06 | 2014-01-07 | 2014-01-08 | 2014-01-09 | 2014-01-10 | 2014-01-11 | 2014-01-12 | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-16 | 2014-01-17 | 2014-01-18 | 2014-01-19 | 2014-01-20 | 2014-01-21 | 2014-01-22 | 2014-01-23 | 2014-01-24 | 2014-01-25 | 2014-01-26

## トレーニング内容
Required Topics
| 2.1) | The Android Platform
http://developer.android.com/develop/index.html
| 2.2) | The Android Development Environment
Development environment setup
http://developer.android.com/sdk/index.html
| 2.3) | Application Fundamentals
Core App Quality Guidelines
http://developer.android.com/distribute/googleplay/quality/core.html
| 2.4) | The Activity Class
Understanding Activity Lifecycle
http://developer.android.com/training/basics/activity-lifecycle/index.html
http://i.stack.imgur.com/leabD.png
Exercise 6.1:
1. Implement a SplashActivity
Override all lifecycle methods (onCreate, onStart, onResume, onPause, onStop, onDestroy, onRestart)
Log each method invocation
2. Save a string in the bundle if the activity is destroyed and log it again upon re-creation
3. Check the lifecycle events during rotation
| 2.5) | The Intent Class
Understanding intents
http://developer.android.com/guide/components/intents-filters.html
| 2.6) | Permissions
Adding permissions
http://developer.android.com/guide/topics/security/permissions.html
Permission groups
Exercise 6.2:
1. Implement a new activity: MainActivity
2. After the creation of the SplashActivity, create an intent which will display the MainActivity.
Destroy the SplashActivity afterwards.
3. Add a permission which will enable the Android application to connect to the internet.
| 2.7) | User Interface Classes - Part I
Building a Simple User Interface
http://developer.android.com/training/basics/firstapp/building-ui.html
Layouts
http://developer.android.com/guide/topics/ui/declaring-layout.html
Starting Another Activity
http://developer.android.com/training/basics/firstapp/starting-activity.html
Exercise 6.3:
1. Follow the Building a Simple User Interface guide
2. Implement a custom View by extinding the View class
3. Draw basic shapes using the android canvas
4. Add input handling to the custom view
| 2.8) | The Fragment Class
Understanding Fragments
http://developer.android.com/guide/components/fragments.html
http://developer.android.com/training/basics/fragments/fragment-ui.html
Exercise 6.4:
1. Add a Fragment on both SplashActivity and MainActivity.
2. Add the Fragment using Layout for SplashActivity
3. Add the Fragment through the Fragment Manager in MainActivity.
Override all lifecycle methods
4. Use fragments to provide flexible layouts for multiple screen configurations (tablet / phone mode, if device is available)
5. Implement Fragment manager to control which fragment is active
| 2.9) | Bitmaps
Bitmap Processing
http://developer.android.com/reference/android/graphics/Bitmap.html
Exercise 6.5:
1. Create a Bitmap from a png inside the Assets folder inside SplashActivity
2. Create a Bitmap from a drawable inside the Resources Folder inside SplashActivity
3. Ensure this Bitmap is properly recycled
| 2.10) | User Interface Classes - Part II
Using the ActionBar
http://www.vogella.com/articles/AndroidActionBar/article.html
http://developer.android.com/training/basics/actionbar/index.html
http://www.androidhive.info/2013/11/android-working-with-action-bar/
UI Best Practices
http://developer.android.com/training/best-ux.html
Exercise 6.6:
1. Add an ActionBar to your application
2. Try implementing a UI navigation system using the ActionBar
2a. Tabbed navigation
2b. Spinner Navigation
3. Customize the ActionBar and handle click events
| 2.11) | Data Storage, File System and Preferences
Saving Data
http://developer.android.com/training/basics/data-storage/index.html
http://developer.android.com/training/basics/data-storage/shared-preferences.html
http://developer.android.com/training/basics/data-storage/files.html
http://developer.android.com/training/basics/data-storage/databases.html
Exercise 6.7:
1. Setup a sample application to save and retrieve data using SharedPreferences (Key-Value Sets)
2. Try reading and writing a text file to Internal Storage (or External Storage if available)
3. Construct a simple SQLite database with multiple tables
3a. Create functions to Insert and delete data to each table
3b. Retrieve and relate data from multiple tables. Experiment with SQL
| 2.12) | Threads, Messages & Thread Pools
https://developer.android.com/training/multiple-threads/index.html
http://developer.android.com/guide/components/processes-and-threads.html
http://developer.android.com/training/multiple-threads/run-code.html
https://developer.android.com/training/multiple-threads/communicate-ui.html
Exercise 6.8:
1. Create a Runnable class
2. Create a Thread Manager object which handles a pool of Thread objects and a queue of Runnable objects
3. Communicate with the UI Thread
4. Load Bitmap using thread
5. Add delay before showing the main activity, show splash screen for 3 seconds
| 2.13) | Networking
https://developer.android.com/training/building-connectivity.html
http://developer.android.com/reference/org/apache/http/client/HttpClient.html
http://developer.android.com/reference/java/net/Socket.html
http://thinkandroid.wordpress.com/2010/03/27/incorporating-socket-programming-into-your-applications/
Exercise 6.9:
1. Try using ConnectivityManager to check connectivity
2. Connect to a webpage via HTTP and download the contents as a String
2a. (Optional) Apply filesystem function from previous exercise and save downloaded data to the filesystem
3. Implement a simple HTTP client
4. Implement Sockets connection
| 2.14) | The ContentProvider Class
http://developer.android.com/guide/topics/providers/content-providers.html
http://developer.android.com/reference/android/content/ContentProvider.html
http://developer.android.com/guide/topics/providers/content-provider-creating.html
Exercise 6.10:
1. Retrieve data from the default Android content Providers
1a. Obtain data from the Contacts Provider
1b. Obtain data from the Calendar Provider
| 2.15) | Build and Deployment
http://developer.android.com/tools/publishing/publishing_overview.html
http://developer.android.com/distribute/googleplay/publish/preparing.html
Clicker Specific Training Topics
| 3.1) | Location and Maps (using Google Play services)
https://developer.android.com/google/play-services/location.html
https://developer.android.com/training/location/index.html
https://developer.android.com/reference/com/google/android/gms/location/package-summary.html
https://developer.android.com/training/location/geofencing.html
Exercise 6.11:
１．Create an app which retrieves the current location from the Google Play services
2. Implement a sample geofencing area
| 3.2) | Camera
http://developer.android.com/training/camera/cameradirect.html
http://developer.android.com/reference/android/hardware/Camera.html
Exercise 6.12:
1. Capture a bitmap using the Camera API
1a. Save the bitmap to file using separate thread
1b. Experiment with the various Camera settings
| 3.3) | Playing Media
http://developer.android.com/guide/topics/media/mediaplayer.html
http://www.vogella.com/articles/AndroidMedia/article.html
Exercise 6.13:
1. Create sample application to play a saved media file
2. Try to play media file from a remote location (web server, etc)
| 3.4) | WebView
Building WebApps in Android's WebView
http://developer.android.com/guide/webapps/webview.html
WebKit Class
http://developer.android.com/reference/android/webkit/package-summary.html
Exercise 6.14:
1. Create a simple web browser using Android's webview
Optional Training Topics

## OtherExercises
Exercises
| # | Exercise | API / tool | Task | Estimated Duration (hrs) | Day | # | Trainee's Notes | Reviewer's Notes
| 1 | Application Lifecycles | - Application | - override all lifecycle methods (onCreate, onStart, onResume, onPause, onStop, onDestroy, onRestart) - log each method invocation - perform an action on the emulator/device to force each call | 1 | D3 | 1
| 2 | UI Mosaic | - layout (XML) | - create a layout with every possible UI control | 1 |  | 2
| 3 | Layout Mosaic | - layout (XML) | - create and application with all 4 layouts | 1 |  | 3
| 4 | Resources |  | - place images inside APK - use images in layouts | 1 | D4 | 4
| 5 | Intents | - Intent - Bundle | - launch browser - call - open dialer - take a picture - send email | 1.5 |  | 5
| 6 | Menu Mosaic | - menu (XML) - Acitivty | - create an exhaustive menu - create a version that uses xml defined menu | 2 |  | 6
| 7 | Dialogs | - Dialog | - launcher for alert dialog - launcher for prompt dialog - launcher for custom dialog - implement managed dialog | 2 |  | 7
| 8 | Preferences Mosaic | - PreferenceActivity | - create a preference activity with all preference option types | 2 | D5 | 8
| 9 | Animation - layout | - android:layoutAnimation (XML) | - display and image that rotates, shrinks, fades, and changes screen position - use android:layoutAnimation | 2 | D6 | 9
| 10 | Animation - view | - Animation - Matrix | - display and image that spins(w/ respect to the y-axis) and expands towards the screen - use Animation object and Matrix | 2 |  | 10
| 11 | AsyncTask | - AsyncTask - ProgressDialog - Handler | - create a loading screen that computes the fibonnaci sequence up to the 1000th place | 2 |  | 11
| 12 | Adapters | - BaseAdapter | - create an adapter from BaseAdapter for the countries of the world | 1 |  | 12
| 13 | Content Providers | - ContentProviders - Cursor | - create own provider APK - access provider data through another app | 2 | D7 | 13
| 14 | HTTP (Get) | - HTTPClient - ThreadSafeClient (*) | - perform an HTTP GET request | 1 |  | 14
| 15 | Service (AIDL) | - Service - NotificationManager - AIDL | - create a service that creates a StatusBar notification with a message - define AIDL for service that passes a message - create an application that invokes service through AIDL | 1.5 |  | 15
| 16 | Play Video | - <VideoView> (XML) | - play a video from SD card | 1 |  | 16
| 17 | Record and Play audio | - MediaPlayer - MediaRecorder | - record and play audio | 1.5 | D8 | 17
| 18 | MediaStore | - MediaStore | - play audio using MediaStore | 1 |  | 18
| 19 | Custom Permissions | - <uses permission> (XML) | - create an application that launches permission-ed app - create a custom permission in app 1 - invoke app 1 with app 2 through custom permission | 0.5 |  | 19
| 20 | Maps & Locations | - LocationManager | - get current location | 1 |  | 20
| 21 | Telephony - SMS | - SmsManager | - send SMS | 0.5 |  | 21
| 22 | Telephony - Call | - TelephonyManager | - log call state | 0.5 |  | 22
| 23 | Homescreen Widget | - WidgetProvider | - create a homescreen widget that is clickable and shows a message | 1.5 |  | 23
[5 empty] | 30.5 | Total
Other Optional Topics
| 24 | Security and Deployment | - keytool - jarsigner - zipalign | - use keytool to create a self-signed certificate - use jarsigner to sign a jar - align the apk using zipalign | 0.5 | N/A
| 25 | OpenGL | - OpenGL | - create a revolving cube | 4
| 26 | Live Folders | - LiveFolders | - create a LiveFolder of the countries of the world | 1
| 27 | Local Search | - android:name="android.app.searchable" (XML) - <searchable> (XML) | - search through a local list of countries of the world | 4
| 28 | Global Search | - Activity.onSearchRequested() | - launch global search | 0.5
| 29 | Speech to Text | - TextToSpeech | - record audio and convert to text | 4
| 30 | Touchscreen | - MotionEvent - Canvas - Activity.onTouchEvent() | - create a multitouch canvas | 2
[5 empty] | 16 | Total